## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | TIC-TAC-TOE WITH UR5e
Enter Company Name in cell B2. | C.A.E | [21 empty] | Key --> AH: Arielle Hui, DL: Daniel Lin, JT: Jovanni Tjuandi, NA: Nethmini Alahakoon
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Project Schedule | Project Start: |  | 2021-06-10
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2021-06-07 | [6 empty] | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 | [6 empty] | 2021-07-05 | [6 empty] | 2021-07-12 | [6 empty] | 2021-07-19 | [6 empty] | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-06-07 to 2021-08-15
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2021-06-07 to 2021-08-15
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Phase 1: Planning
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Project Scope | AH, JT, DL, NA | 100% | 2021-06-10 | 2021-06-10 | 1
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Initial Milestones and Deliverables | NA | 100% | 2021-06-10 | 2021-06-12 | 3
| Change Management Plan | JT | 100% | 2021-06-10 | 2021-06-15 | 6
| Scope Management Plan | AH, JT, DL, NA | 100% | 2021-06-10 | 2021-06-12 | 3
| Schedule Management Plan (initial Gantt Chart) | NA | 100% | 2021-06-10 | 2021-06-15 | 6
Quality Management Plan | Quality Management Plan | JT | 100% | 2021-06-10 | 2021-06-15
| Risk Management Plan | DL | 100% | 2021-06-10 | 2021-06-15
| Organisational Structure | AH | 100% | 2021-06-10 | 2021-06-15
| Staffing Management Plan | AH | 100% | 2021-06-10 | 2021-06-15
| Communication Management Plan | DL | 100% | 2021-06-10 | 2021-06-15
| Project Management Plan Report | AH, JT, DL, NA | 100% | 2021-06-15 | 2021-06-18
| Requirements expected from project (User stories) | AH, JT, DL, NA | 100% | 2021-06-24 | 2021-06-30
| Technical Specification for proposed solution | AH, JT, DL, NA | 100% | 2021-06-24 | 2021-06-30
| Work Breakdown Structure | AH, NA | 100% | 2021-06-29 | 2021-07-01
| Baseline Schedule | AH | 100% | 2021-06-29 | 2021-07-01
| Test Plan | DL, JT | 100% | 2021-06-28 | 2021-07-01
| Requirements and Specifications report | AH, JT, DL, NA | 100% | 2021-06-15 | 2021-07-02
| Update Gantt Chart | NA | 100% | 2021-07-01 | 2021-07-05
| Select material to use for Game Board & Pieces | AH, JT, DL, NA | 100% | 2021-06-13 | 2021-07-05
| Purchase materials that’s within budget | AH, JT, DL, NA | 0% | 2021-06-13 | 2021-07-05
| Publisher/ Subscriber Diagram | AH, JT, DL, NA | 100% | 2021-07-12 | 2021-07-21
| Program Flowchart | AH, JT, DL, NA | 100% | 2021-07-12 | 2021-07-21
| QT Viability Research | AH, JT, DL, NA | 100% | 2021-07-12 | 2021-07-21
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Phase 2: Core System Functionality
| Game Piece and Board Design | AH, JT, DL, NA | 55% | 2021-07-05 | 2021-07-09 | 5
| Game Piece and Board Construction | AH, JT, DL, NA | 0% | 2021-07-05 | 2021-07-10 | 6
| Game Piece and Board Testing | AH, JT, DL, NA | 0% | 2021-07-05 | 2021-07-08 | 4
| Game Piece and Board Design Simulation | NA | 40% | 2021-07-05 | 2021-08-02 | 29
| User Interface Design | AH | 0% | 2021-07-08 | 2021-07-29 | 22
| User Interface Programming | AH | 0% | 2021-07-08 | 2021-07-31
| User Interface Testing | AH | 0% | 2021-07-08 | 2021-08-01 | 25
| User Interface Finalisation | AH | 0% | 2021-07-12 | 2021-08-02
| Robot Waiting Programming | JT, NA | 0% | 2021-07-07 | 2021-07-23
| Robot “Pick Piece” Programming | JT, NA | 0% | 2021-07-07 | 2021-07-24
| Robot “Place Piece” Programming | JT, NA | 0% | 2021-07-07 | 2021-07-25
| Smooth Operation of Arm | JT, NA | 0% | 2021-07-12 | 2021-07-26
| Piece Type and Quantity Detection | DL | 0% | 2021-07-07 | 2021-07-29
| Piece Location Detection | DL | 0% | 2021-07-09 | 2021-08-02
| Robot Play Arena and User Arena Specification | NA | 100% | 2021-07-07 | 2021-07-07
| Safety Plane Set-Up | NA | 100% | 2021-07-08 | 2021-07-09
| Safety Plane Testing | NA | 100% | 2021-07-12 | 2021-07-12
Maximum Speed and Acceleration Set-Up | Maximum Speed and Acceleration Set-Up | NA | 100% | 2021-07-13 | 2021-07-13
| Test: Identification of Piece Type and Location | JT | 0% | 2021-07-07 | 2021-07-26
| Test: Pieces Correctly Positioned | NA | 0% | 2021-07-09 | 2021-07-24
| Test: Accessibility and Ergonomics | NA | 0% | 2021-07-09 | 2021-07-27
| Test: User Interface | NA | 0% | 2021-07-08 | 2021-07-25
| Test: Safety Features | DL | 0% | 2021-07-07 | 2021-07-20
| Test: Movement Quality | NA | 0% | 2021-07-07 | 2021-07-25
| Test: Game Piece Quality | NA | 0% | 2021-07-07 | 2021-07-24
Sample phase title block | Phase 3: Full Sysem Functionality
| Correct Piece Placement Check | DL | 55% | 2021-07-14 | 2021-07-16 | 3
| Rule Violation Check | DL | 45% | 2021-07-19 | 2021-07-26 | 8
| Board State Saving | DL | 0% | 2021-07-27 | 2021-07-29 | 3
| Game Time-Out System | AH | 0% | 2021-07-29 | 2021-07-30 | 2
| Logic for “Easy” Difficulty | JT | 100% | 2021-07-17 | 2021-07-20 | 4
| Logic for “Hard” Difficulty | JT | 80% | 2021-07-18 | 2021-07-20
| Winning Algorithm | JT | 100% | 2021-07-20 | 2021-07-30
| Overall Winner Logic | JT | 0% | 2021-07-21 | 2021-07-30
| Implementation of Algorithm in C++ | JT | 0% | 2021-07-21 | 2021-07-30
| Test: Difficulty Levels | NA | 0% | 2021-07-28 | 2021-07-30
| Test: Rule Violations | NA | 0% | 2021-07-29 | 2021-08-02
| Test: Troubleshooting | NA | 0% | 2021-07-28 | 2021-08-06
Test: | Test: Game Winner Check | NA | 0% | 2021-07-26 | 2021-08-02
| Test: Game Time Limit | NA | 0% | 2021-07-28 | 2021-08-02
Sample phase title block | Phase 4: Complete System Integration
| Basic System Integration | AH, JT, DL, NA | 0% | 2021-07-27 | 2021-08-11 | 16
| Full System Integration | AH, JT, DL, NA | 0% | 2021-07-27 | 2021-08-11 | 16
| Final Testing | AH, JT, DL, NA | 0% | 2021-07-27 | 2021-08-11 | 16
This is an empty row | Phase 5: Testing and Documentation
| Test: Final Comprehensive Testing of Full Integrated System | AH, JT, DL, NA | 0% | 2021-08-11 | 2021-08-13
| User Manual Creation | NA | 45% | 2021-07-28 | 2021-08-13
| Safety Documentation Creation | NA | 100% | 2021-07-28 | 2021-08-13
| Documentation Creation | NA | 50% | 2021-07-28 | 2021-08-13
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule.